## QA Summary
Bihar District Intelligence & Recommendation System — Final QA & Validation Documentation
Final pre-submission checklist covering data, model, DAX, visuals, interactions, usability and documentation
Project status | All six report pages and page navigation have been completed; documentation package is now being finalized.
Primary QA principle | Validate correctness first, then usability and presentation.
Critical checks | District relationships, aggregation logic, rainfall variance direction, education year context, sex-ratio interpretation, slicer/navigation behavior.
Evidence limitation | This workbook records validation checks supported by the completed project workflow. Checks requiring direct PBIX interaction should be marked/confirmed in the PBIX before final submission.

## Data QA
ID | Check | Expected Result | Validation / Evidence | Status | Priority | Final Action
D01 | District count | 38 Bihar districts represented in district dimension/facts. | Project workflow and ShapeMap use 38 districts. | PASS | High | No action unless PBIX shows an orphan/missing district.
D02 | District_ID consistency | Fact table district IDs match Dim_District IDs. | District_ID is the common model key documented across facts. | PASS | Critical | Confirm relationship view before final submission.
D03 | District names | Consistent district naming in visuals/slicers/map. | District dimension is the standardized reference. | PASS | High | Use Dim_District names for slicers.
D04 | Population period | Population reference year is clearly identified as 2011. | Source table uses 2011 reference data. | PASS | High | Display/mention period where necessary.
D05 | Agriculture scope | Agriculture period/crop scope is understood before interpreting trends. | Reviewed source contains 2023-2024 and one crop; broader model may contain additional prepared data. | PASS WITH NOTE | High | Do not claim unsupported multi-crop conclusions from the reviewed source.
D06 | Education years | 2019-20, 2020-21 and 2021-22 remain distinct. | Final education data contains district × academic-year records. | PASS | Critical | Ensure year slicers/context are respected.
D07 | Rainfall period | Rainfall data is identified as 2026. | Source is district-wise 2026 rainfall. | PASS | High | Label rainfall visuals appropriately.
D08 | Missing/blank rows | Non-district/total rows do not inflate district analysis. | Education cleaning removed totals/non-district rows during project workflow. | PASS | High | Recheck after any refresh.

## Model QA
ID | Check | Expected Result | Validation / Evidence | Status | Priority | Final Action
M01 | Dim_District uniqueness | District_ID is unique on the 1-side. | Dimension is designed as one row per district. | PASS | Critical | Confirm no duplicate District_ID in Power Query/model.
M02 | Relationship cardinality | Dim_District 1:* to each fact table. | Documented model design uses one-to-many district relationships. | PASS | Critical | Confirm in Model view.
M03 | Filter direction | District dimension filters fact tables. | Single-direction design is documented. | PASS | High | Confirm no unintended bidirectional relationships.
M04 | No unnecessary fact-to-fact relationships | Facts remain independent through the dimension. | Separate domain facts are documented. | PASS | High | Remove accidental fact-to-fact relationships if any.
M05 | Fact grain | Each fact retains its own domain grain. | Population, agriculture, education and rainfall have different grains. | PASS | Critical | Validate before changing visuals.

## DAX & Aggregation QA
ID | Check | Expected Result | Validation / Evidence | Status | Priority | Final Action
X01 | Rainfall variance sign | Positive when Actual > Normal; negative when Actual < Normal. | Project formula uses Actual − Normal. | PASS | Critical | Keep this definition.
X02 | Rainfall deviation % | Use rate/average, never SUM. | Deviation is non-additive. | PASS | Critical | Check visual aggregation.
X03 | Population | Population count can SUM in appropriate context. | Documented aggregation guidance. | PASS | High | Avoid averaging population for total KPIs.
X04 | Agriculture production | Production can SUM across distinct records. | Production is additive at appropriate grain. | PASS | High | Check no duplicate records.
X05 | Agriculture yield | Yield is treated as a rate, not SUM. | Yield requires average or weighted treatment. | PASS | High | Prefer weighted yield when combining unequal areas.
X06 | Education schools | School counts respect academic-year context. | Repeated years must not be unintentionally combined. | PASS | Critical | Test each year selection.
X07 | Education teachers | Teacher counts respect academic-year context. | Same principle as school counts. | PASS | Critical | Test each year selection.
X08 | Sex ratio | 921 means 921 females per 1,000 males, not 921%. | Percentage display divides ratio by 1,000. | PASS | High | Keep ratio and percentage labels clear.
X09 | Literacy rate | Treat as percentage/rate, not SUM. | Rate is non-additive. | PASS | High | Use appropriate average/measure.

## Visual & Interaction QA
ID | Check | Expected Result | Status | Priority | Test Procedure
V01 | Home navigation buttons | Each button opens the intended report page. | TO CONFIRM IN PBIX | Critical | Click every button from Home.
V02 | Back/navigation behavior | Users can return to Home/previous navigation path as designed. | TO CONFIRM IN PBIX | High | Test every page transition.
V03 | District slicer | Selecting a district updates dependent visuals. | TO CONFIRM IN PBIX | Critical | Select 3 different districts and compare KPIs.
V04 | Crop slicer | Selecting a crop filters agriculture visuals only as intended. | TO CONFIRM IN PBIX | High | Select multiple crops and clear selection.
V05 | Map interaction | Map responds correctly to district selection/visual interactions. | TO CONFIRM IN PBIX | High | Click multiple districts; verify other visuals.
V06 | KPI consistency | KPI cards agree with underlying chart/filter context. | TO CONFIRM IN PBIX | Critical | Cross-check card values against table/chart totals.
V07 | No visual overlap | Text, shapes, buttons and charts do not overlap or hide content. | TO CONFIRM IN PBIX | High | Inspect each page at report and presentation view.
V08 | Titles/labels | Every visual clearly communicates metric and period. | TO CONFIRM IN PBIX | High | Review all titles, axis labels, legends and units.
V09 | Tooltips | Important visuals show useful context when hovered. | TO CONFIRM IN PBIX | Medium | Hover over key charts and map.
V10 | Slicers clear/reset | Clear selection returns page to intended default state. | TO CONFIRM IN PBIX | Medium | Clear each slicer and verify defaults.

## UX & Design QA
ID | Check | Expected Result | Status | Priority | Final Action
U01 | Consistent theme | All pages use the selected simple theme consistently. | TO CONFIRM | High | Review colors, fonts, cards and spacing.
U02 | Readable KPI row | KPI values are prominent and not crowded. | TO CONFIRM | High | Check desktop presentation at 100%.
U03 | Visual hierarchy | Most important insight is visually dominant. | TO CONFIRM | High | Reduce unnecessary decoration if needed.
U04 | Map readability | Bihar ShapeMap is legible and district boundaries/legend are clear. | TO CONFIRM | High | Check color contrast and legend meaning.
U05 | Whitespace | Pages are neither overcrowded nor excessively empty. | TO CONFIRM | Medium | Review each page as a portfolio reviewer.
U06 | Units | mm, %, MT, kg/ha, population and teacher/school counts are clearly labeled. | TO CONFIRM | High | Check titles/tooltips/data labels.
U07 | Accessibility | Text has sufficient contrast and interactive elements are identifiable. | TO CONFIRM | Medium | Review contrast and labels.

## Refresh & Reliability QA
ID | Check | Expected Result | Status | Final Action
R01 | Refresh all queries | All queries refresh without errors. | TO CONFIRM | Refresh in Power BI Desktop and record any errors.
R02 | No broken sources | Source paths/connections resolve on the final machine. | TO CONFIRM | Check Data source settings.
R03 | Data types | Numeric fields remain numeric; dates/years remain appropriate types. | TO CONFIRM | Inspect Power Query and Model views.
R04 | No unexpected duplicates | Refresh does not duplicate fact rows. | TO CONFIRM | Compare row counts before/after refresh if sources change.
R05 | Performance | Report pages load and respond reasonably. | TO CONFIRM | Use Performance Analyzer for slow visuals.
R06 | Save/reopen test | PBIX reopens with visuals, relationships and measures intact. | TO CONFIRM | Close/reopen final PBIX before submission.

## Final Sign-off
Area | Current State | Required Before Submission | Owner Action | Sign-off
Data quality | Core data preparation completed. | Run final refresh and spot checks. | Project owner | Pending
Model | Star/district-centered model documented. | Verify relationship view once. | Project owner | Pending
DAX | Measures documented and aggregation rules defined. | Spot-check KPI values. | Project owner | Pending
Visuals | All pages designed and navigation activated. | Run visual/interaction checklist. | Project owner | Pending
Business insights | Evidence-based findings report created. | Ensure insights match final PBIX state. | Project owner | Pending
Documentation | Data Dictionary, DAX, lineage, ETL, model, visualization and insights docs created. | Check filenames/versioning and package together. | Project owner | Pending
Portfolio readiness | Project is ready for final presentation packaging. | Create README/case study and presentation after QA. | Project owner | Pending

## README
Item | Details
Purpose | Final QA checklist for the BDDIP Power BI portfolio project.
How to use | Work through each sheet, complete all items marked TO CONFIRM, then update the Status/Sign-off fields.
Critical items | Relationship cardinality, District_ID consistency, rainfall variance sign, education year context, KPI correctness and navigation should be treated as highest priority.
Important distinction | PASS means supported by project documentation/source evidence; TO CONFIRM means it requires a direct check in the final PBIX/report.
Final sequence | Complete QA → refresh/reopen PBIX → resolve issues → freeze final PBIX → create README/case study → create final presentation.